## Gantt Chart
Gantt Chart: UniGreen Project (semester Weeks 6–10)
Monday of semester Week 6: |  |  | 2026-10-12 |  |  | How to edit: change BLUE cells only. Start/End use half-weeks: 8 = Week 8 Mon–Wed, 8.5 = Week 8 Thu–Sun. Bars move automatically. The red column is today.
ID | Task | Who | Start | End | Weeks | Status | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10
[7 empty] | Mon–Wed | Thu–Sun | Mon–Wed | Thu–Sun | Mon–Wed | Thu–Sun | Mon–Wed | Thu–Sun | Mon–Wed | Thu–Sun
[7 empty] | 2026-10-12 | 2026-10-15 | 2026-10-19 | 2026-10-22 | 2026-10-26 | 2026-10-29 | 2026-11-02 | 2026-11-05 | 2026-11-09 | 2026-11-12
[7 empty] | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5
1 | Planning & Analysis
1.1 | Write project proposal | All | 6 | 6 | 0.5 | Done
1.2 | Gather requirements | All | 6 | 7 | 1.5 | Done
1.3 | Draw use case diagram | All | 8 | 8 | 0.5 | Done
1.4 | Draw DFD (Level 0 & 1) | All | 8 | 8 | 0.5 | Done
1.5 | Make WBS & Gantt chart | All | 8 | 8 | 0.5 | Done
2 | Design
2.1 | Design database (ERD) | Database | 7 | 7.5 | 1 | Done
2.2 | Design system architecture | Backend | 7 | 7.5 | 1 | Done
2.3 | Design screens in Figma | Frontend | 8 | 8 | 0.5 | Planned
3 | Backend (FastAPI)
3.1 | Sign up, login & logout | Backend | 7 | 8 | 1.5 | Done
3.2 | Bins, recycling log & points | Backend | 8.5 | 9 | 1 | Planned
3.3 | Pickups & bin reports | Backend | 9 | 9 | 0.5 | Planned
3.4 | Rewards & coupons | Backend | 9.5 | 9.5 | 0.5 | Planned
3.5 | Admin features & reports | Backend | 9.5 | 10 | 1 | Planned
4 | Frontend & UI
4.1 | Base layout & green theme | Frontend | 8 | 8.5 | 1 | In progress
4.2 | Student pages | Frontend | 8.5 | 9.5 | 1.5 | Planned
4.3 | Admin pages & charts | Frontend | 9.5 | 10 | 1 | Planned
4.4 | Splash screen (if time allows) | Frontend | 10 | 10 | 0.5 | Planned
5 | Testing
5.1 | Unit & API testing | All | 9 | 10 | 1.5 | Planned
5.2 | Mobile & browser testing | All | 10 | 10 | 0.5 | Planned
5.3 | Fix bugs | All | 10 | 10.5 | 1 | Planned
6 | Deployment & Docs
6.1 | Deploy online | Backend | 10.5 | 10.5 | 0.5 | Planned
6.2 | Final report & user guide | All | 9.5 | 10.5 | 1.5 | Planned
6.3 | Presentation & viva demo | All | 10.5 | 10.5 | 0.5 | Planned
Colours (WBS parts):
1 | Planning & Analysis
2 | Design
3 | Backend (FastAPI)
4 | Frontend & UI
5 | Testing
6 | Deployment & Docs
Note on D2: Assumption: semester Week 8 = week of 26 Oct 2026. Change this date and all dates update.